PROJECT REPORT

CUSTOMER SUPPORT TICKET PRIORITY PREDICTION AND AUTOMATED ASSIGNMENT SYSTEM USING AGENTFORCE

# 1. Introduction

Project planning describes how the work is organized, who does it, and in what order. This project follows the Agile methodology with short sprints. The work is broken down as Epics, then User Stories, then Story Points, and progress is tracked using sprint velocity and a burndown chart.

# 2. Planning Approach

- Agile methodology with sprint-based execution.

- Epics to Stories to Story Points for breaking down and estimating work.

- Velocity (story points completed per sprint) used for estimation.

- Six sprints of one week (6 working days) each.

# 3. Team Roles

| Team member | Responsibility |
| --- | --- |
| Member 1 | Environment setup and Agentforce subagent configuration (Sprint 1 and 4) |
| Member 2 | Data modeling and task and assignment automation (Sprint 2 and 4) |
| Member 3 | Account and Contact relationships and SLA management (Sprint 2 and 5) |
| Member 4 | Flow logic, priority classification and conversational support (Sprint 3 and 6) |

# 4. Product Backlog

| Sprint | Epic | Story | User story / task | Pts | Priority | Owner |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Developer setup | USN-1 | As a system administrator, I want to configure the Salesforce environment for Support Ticket Intelligence so that the automation can be developed | 3 | High | Member 1 |
| 2 | Data modeling | USN-2 | As an admin, I want to create the Support Ticket Intelligence object with required fields and relationships so that ticket information is stored systematically | 5 | High | Member 2 |
| 2 | Data modeling | USN-3 | As a support user, I want tickets associated with Accounts and Contacts so that the latest customer ticket can be identified | 3 | High | Member 3 |
| 3 | Automation | USN-4 | As a support agent, I want an Auto-Launched Flow to retrieve the latest ticket and analyze its description so that priority is determined automatically | 5 | High | Member 4 |
| 3 | Automation | USN-5 | As a support agent, I want tickets classified as High, Medium or Low so that critical issues receive attention first | 5 | High | Member 4 |
| 4 | Agentforce and automation | USN-6 | As an AI agent, I want to analyze ticket details and trigger the backend Flow so that manual prioritization is reduced | 8 | High | Member 1 |
| 4 | Task and assignment | USN-7 | As a support manager, I want High tickets to create an urgent task and assign the support level so that critical tickets are handled quickly | 5 | High | Member 2 |
| 5 | SLA management | USN-8 | As a support manager, I want the system to check SLA breach risk for older unresolved tickets | 5 | Medium | Member 3 |
| 6 | Conversational support | USN-9 | As a support user, I want to give an Account Name to Agentforce and receive ticket Id, priority, assigned agent and action message | 5 | Medium | Member 4 |

# 5. Sprint Schedule and Estimation

| Sprint | Duration | Planned timeline | Focus | Story points |
| --- | --- | --- | --- | --- |
| Sprint 1 | 6 days | Week 1 | Developer org and environment setup | 3 |
| Sprint 2 | 6 days | Week 2 | Custom object, fields, Account and Contact links | 8 |
| Sprint 3 | 6 days | Week 3 | Auto-Launched Flow and priority classification | 10 |
| Sprint 4 | 6 days | Week 4 | Agentforce subagent, Flow action, urgent task and assignment | 13 |
| Sprint 5 | 6 days | Week 5 | SLA risk check | 5 |
| Sprint 6 | 6 days | Week 6 | Conversational output, testing and documentation | 5 |
| Total |  | 6 weeks |  | 44 |

# 6. Velocity Calculation

Total story points = 3 + 8 + 10 + 13 + 5 + 5 = 44. Number of sprints = 6. Average velocity = 44 / 6 = about 7.3 story points per sprint.

Using the average velocity, the remaining work after any sprint can be estimated. For example, if 8 points are completed in Sprint 2, the remaining 33 points need roughly 4 to 5 more sprints, which matches the plan.

# 7. Project Tracker and Burndown Chart

| Sprint | Points planned | Points completed | Remaining after sprint |
| --- | --- | --- | --- |
| Sprint 1 | 3 | 3 | 41 |
| Sprint 2 | 8 | 8 | 33 |
| Sprint 3 | 10 | 10 | 23 |
| Sprint 4 | 13 | 13 | 10 |
| Sprint 5 | 5 | 5 | 5 |
| Sprint 6 | 5 | 5 | 0 |

Figure 1: Sprint burndown chart

# 8. Milestones

| Milestone | Description | Deliverable |
| --- | --- | --- |
| M1 | Salesforce account created and activated | Developer org ready |
| M2 | Data management: custom object and fields | Support Ticket Intelligence object |
| M3 | Flow logic complete | Support_Ticket_Intellegence flow (active) |
| M4 | Agentforce configuration | Subagent and Flow action |
| M5 | Testing and documentation | Test results and project report |

# 9. Risk Management

| Risk | Impact | Response |
| --- | --- | --- |
| Agentforce not enabled in the org | High | Enable through Salesforce Go in Sprint 1 |
| Flow logic errors | Medium | Debug with test records before linking to the agent |
| Scope growth | Medium | Keep extra ideas in future scope; follow the backlog |
| Time shortage | Medium | Move Medium-priority stories to the next sprint |

# 10. Testing Plan

- Unit testing of the Flow with sample tickets for High, Medium and Low descriptions.

- Integration testing of the Agentforce action with the Flow in Conversation Preview.

- Verification of task creation and assignment for High-priority tickets.